## Summary
Milano Transit Live — progress by phase
Counts come from the Roadmap sheet.
Phase | Done | In progress | Next | Planned | Later | Waiting on Giovanni | Total | % done
0 Foundation | 20 | 0 | 0 | 0 | 0 | 2 | 22 | 90.91%
1 M3 playable | 4 | 0 | 4 | 10 | 0 | 1 | 19 | 21.05%
2 Calendar | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 0%
3 Analysis mode | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0%
4 Metro in depth | 0 | 0 | 0 | 0 | 3 | 1 | 4 | 0%
5 Buses | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0%
6 Driver rules | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0%
7 Trams | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0%
Licenses & hosting | 0 | 0 | 6 | 1 | 0 | 0 | 7 | 0%
All phases | 24 | 0 | 10 | 16 | 7 | 4 | 61 | 39.34%

## Roadmap
Milano Transit Live — roadmap
Edit Status and Who with the dropdowns. Add new rows at the bottom; the Summary updates by itself.
# | Phase | Area | Item | Status | Who | Notes
1 | 0 Foundation | Data | ATM timetable (GTFS) loaded, service day 03:00–02:59 | Done | Claude | One weekday timetable used for Mon–Fri
2 | 0 Foundation | Map | Satellite, Hybrid and OSM maps + rail tracks overlay | Done | Claude
3 | 0 Foundation | Network | Every metro, tram and bus vehicle moving as a dot from the timetable | Done | Claude | Trams and most buses only at timetable level
4 | 0 Foundation | Network | 30 s stop at every metro station, 15 s at bus stops | Done | Both
5 | 0 Foundation | M3 | All M3 tracks and junctions drawn from OpenStreetMap, right-hand running | Done | Both | Porta Romana–Repubblica stacked tracks allowed to overlap
6 | 0 Foundation | M3 | San Donato rules: arrivals on platform 3, one train per tail, cab change, departures from 1/2 with 30 s–2 min wait | Done | Both | 0 tail clashes, 0 late departures
7 | 0 Foundation | M3 | Comasina terminal and 2 trains overnight in the tails of both termini | Done | Both | One evening train waits 7 min on the arrival platform (no other place)
8 | 0 Foundation | M3 | Depot: through tracks, parking only on tracks ≥ 115 m, 15 km/h, one train per track | Done | Both | 20 parking places
9 | 0 Foundation | M3 | Test loop (anello di prova) on demand from every depot place | Done | Both | 20 of 20 places
10 | 0 Foundation | M3 | Real fleet: 24 trains with units, type and year | Done | Both | Peak 23 trains at 07:32
11 | 0 Foundation | M3 | Platform labels 1–2–3, platform diagram, departure platform picker | Done | Claude
12 | 0 Foundation | M3 | Player order: train from Rogoredo arrives on platform 2 and reverses there | Done | Claude | Only if platform 2 is free when ordered
13 | 0 Foundation | M4 | M4 tracks, San Cristoforo depot, real fleet 4401–4447 | Done | Both
14 | 0 Foundation | M1 | M1 trains on real tracks (10 stop patterns), platforms | Done | Claude | Depot movements later
15 | 0 Foundation | Stations | Station boards in Italian, "in arrivo", red "Servizio terminato" | Done | Both | M3 in arrivo < 1:30, M4 < 30 s
16 | 0 Foundation | Buses | Line 130: 7 buses, 18 m articulated, H stops | Done | Claude
17 | 0 Foundation | Buses | Line 64: 11 buses, 12 m, ATM-style stop display + stop timetable | Done | Claude
18 | 0 Foundation | Editor | Track editor: track use, 5 signal types, draw missing tracks, export | Done | Claude
19 | 0 Foundation | Editor | Your 7 M3 signals saved into the build | Done | Giovanni
20 | 0 Foundation | Game | Admin / Player modes, M3 control panel with delay colours | Done | Claude
21 | 0 Foundation | Editor | Mark the depot X tracks as "movements only, no parking" | Waiting on Giovanni | Giovanni | Send the export, Claude rebuilds
22 | 0 Foundation | Editor | Place the 2 stops on the anello di prova | Waiting on Giovanni | Giovanni | Signal type "stop"
23 | 1 M3 playable | Project | Public GitHub repo, project split into files | Next | Claude | Open from day one
24 | 1 M3 playable | Project | Automatic tests (tails, depot, late departures) run on every change | Next | Claude
25 | 1 M3 playable | Engine | Live simulation engine in the browser (JavaScript, background worker) | Planned | Claude | Replaces the precomputed day
26 | 1 M3 playable | Signals | Block sections built from your signals | Planned | Both
27 | 1 M3 playable | Signals | Junctions locked for a route before a train passes | Planned | Claude
28 | 1 M3 playable | Signals | Player sees block signals and all signals | Planned | Claude
29 | 1 M3 playable | Engine | Every delay records its cause (what should happen / what happened / why) | Planned | Claude
30 | 1 M3 playable | Game | First scenario: fault San Donato–Rogoredo | Planned | Both
31 | 1 M3 playable | Game | Player controls: hold a train, turn back at Rogoredo, close a section, replacement bus | Planned | Both | Chiusura tratte
32 | 1 M3 playable | Game | Score: minutes of delay + runs cancelled | Planned | Claude | No passenger model
33 | 2 Calendar | Data | Real dates: Saturday, Sunday, holidays from the timetable feed | Planned | Claude | Date picker replaces Lun–Ven
34 | 2 Calendar | Data | Christmas, New Year's Eve and reduced-service days | Planned | Both | From your PDFs if the feed does not cover them
35 | 3 Analysis mode | Analysis | Plan vs what happened, with the cause of every delay | Planned | Claude
36 | 3 Analysis mode | Analysis | Indicators: gaps between trains, lateness, runs lost | Planned | Claude
37 | 3 Analysis mode | Analysis | Compare two what-if runs and export a report | Planned | Claude
38 | 4 Metro in depth | M1 | M1 depots and terminal movements | Later | Both
39 | 4 Metro in depth | M2 | M2 tracks, terminals, depots, fleet | Later | Both
40 | 4 Metro in depth | M4 | Linate track use marks | Waiting on Giovanni | Giovanni
41 | 4 Metro in depth | M5 | M5 tracks, terminals, depot, fleet | Later | Both
42 | 5 Buses | Buses | Traffic model from open traffic data | Later | Both | Check the traffic data license
43 | 5 Buses | Buses | More lines with stop displays, bus breakdowns | Later | Both
44 | 6 Driver rules | Drivers | Shifts, breaks, driver change at the terminus, "no driver" events | Later | Both | Advanced level
45 | 7 Trams | Trams | Tram tracks, street junctions, depots | Later | Both | The biggest manual job
46 | Licenses & hosting | License | Code under GPL-3.0 | Next | Giovanni | Copies must stay open source
47 | Licenses & hosting | License | Credits: Comune di Milano timetable, OpenStreetMap (ODbL), Esri, CARTO | Next | Claude | Check the GTFS dataset license line once
48 | Licenses & hosting | License | "Unofficial, not affiliated with ATM", no ATM logo | Next | Claude
49 | Licenses & hosting | Map | Free ArcGIS Developer account for satellite imagery | Next | Giovanni | No ads, < 1 million tiles a month
50 | Licenses & hosting | Map | Satellite imagery only over Lombardy, street map elsewhere | Next | Claude | Cuts tile use
51 | Licenses & hosting | Map | Free CARTO key for the street map | Next | Giovanni | Non-commercial, 5 million tiles a month
52 | Licenses & hosting | Hosting | Host free on GitHub Pages, no ads, no money inside | Planned | Both
53 | 1 M3 playable | Game | ZUB San Donato–Rogoredo (one train per track between stations) | Done | Claude
54 | 1 M3 playable | Game | Close San Donato–Rogoredo: trains stop, San Donato holds, short turns at Rogoredo | Done | Claude | Reopening still jumps back to the timetable
55 | 1 M3 playable | Engine | Live engine steps 1–2: network export, physics following the plan | Done | Claude | 0 runs late
56 | 1 M3 playable | Signals | Pixel-art M3 signals (red / red + white / white) | Done | Claude
57 | 1 M3 playable | Game | Reopening a closed section with real recovery | Next | Claude
58 | 1 M3 playable | Engine | Traction from power and mass (2080 kW, 163–265 t), load by time of day | Next | Claude | From the Wikipedia data Giovanni sent
59 | 1 M3 playable | Engine | Line speed limits: 80 km/h only San Donato–Rogoredo, rest to confirm | Waiting on Giovanni | Giovanni
60 | 1 M3 playable | Game | Turnback points: Maciachini, Sondrio, Centrale FS, Repubblica, Porta Romana, Lodi TIBB, Brenta (towards Comasina only), Rogoredo FS | Planned | Both | docs/m3-turnback-points.md
61 | 1 M3 playable | Game | Close any section between two turnback points (Lodi–Rogoredo, Lodi–San Donato, Porta Romana–Repubblica, ...) with shuttles on both sides | Planned | Claude | Compute every possibility

## Lists (hidden)
0 Foundation
1 M3 playable
2 Calendar
3 Analysis mode
4 Metro in depth
5 Buses
6 Driver rules
7 Trams
Licenses & hosting